## Dashboard
Team | Committed / Completed Ratio |  |  |  |  | Planning Health |  | Team Composition | [5 empty] | Size Health | Dedication Health | Family Fun
| Last 4 Sprints |  |  |  | Sparkline |  |  | Core | Dev | Test | Analyst | Total | Split |  |  | Last | Days
Team One | 85.71% | 75% | 82.61% | 71.43% |  | Good | 1 | 2 | 4 | 2 | 1 | 7 | 0 | Ideal | 0% | 2012-09-06 | 42
| 2012-07-30 | 2012-08-13 | 2012-08-27 | 2012-09-10
Team Two | 100% | 92.31% | 115.4% | 100% |  | Excellent | 0 | 3 | 3 | 3 | 2 | 8 | 2 | Ideal | 18.18% | 2012-08-23 | 56
| 2012-08-01 | 2012-08-15 | 2012-08-29 | 2012-09-12
Team Three | 95% | 72.73% | 100% | 78.57% |  | Good | 1 | 3 | 8 | 2 | 1 | 11 | 2 | Too Big | 14.29% | 2012-08-15 | 64
| 2012-08-07 | 2012-08-21 | 2012-09-04 | 2012-09-18
Team Four | 100% | 77.78% | 83.33% | 80% |  | Excellent | 0 | 3 | 2 | 2 | 0 | 4 | 1 | Ideal | 14.29% | 2012-09-10 | 38
| 2012-08-07 | 2012-08-21 | 2012-09-04 | 2012-09-18
Team Five | 82.35% | 116.7% | 100% | 100% |  | Excellent | 0 | 3 | 3 | 2 | 2 | 7 | 5 | Ideal | 50% | 2012-10-15 | 3
| 2012-08-08 | 2012-08-22 | 2012-09-05 | 2012-09-19
Team Six | 100% | 90% | 80% | 100% |  | Excellent | 0 | 2 | 7 | 2 | 2 | 11 | 2 | Too Big | 15.38% | 2012-09-15 | 33
| 2012-07-17 | 2012-08-01 | 2012-08-16 | 2012-08-30
Team Seven | 0% | 68.75% | 33.33% | 100% |  | Watch | 3 | 3 | 2 | 1 | 2 | 5 | 3 | Ideal | 37.5% | 2012-07-27 | 83
| 2012-08-01 | 2012-08-15 | 2012-08-29 | 2012-09-13
Team Eight | 100% | 100% | 91.67% | 79.31% |  | Excellent | 0 | 3 | 6 | 4 | 2 | 12 | 4 | Too Big | 26.67% | 2012-08-31 | 48
| 2012-08-01 | 2012-08-16 | 2012-08-29 | 2012-09-12
Team Nine | 100% | 85.71% | 75% | 100% |  | Excellent | 0 | 2 | 2 | 2 | 1 | 5 | 4 | Ideal | 57.14% | 2012-08-15 | 64
| 2012-07-24 | 2012-08-14 | 2012-08-28 | 2012-09-11
Team Ten | 100% | 100% | 137.5% | 92.31% |  | Good | 1 | 3 | 5 | 2 | 1 | 8 | 1 | Ideal | 9.091% | 2012-09-15 | 33
| 2012-07-31 | 2012-08-14 | 2002-08-28 | 2012-09-11
Team Eleven | 83.33% | 100% | 70% | 66.67% |  | Average | 2 | 3 | 4 | 1 | 1 | 6 | 2 | Ideal | 22.22% | 2012-08-23 | 56
| 2012-09-05 | 2012-09-05 | 2012-09-19 | 2012-09-19
Thresholds | [5 empty] | 75% | [7 empty] | 9 | 33% |  | 60
125%
Formulas:
Days = TODAY()-[Family Fun]

## Team 1
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 1 | 17 | 2012-08-28 | 2012-09-10 | 14 | 10 | 71.43%
Release 1 | 16 | 2012-08-14 | 2012-08-27 | 23 | 19 | 82.61%
Release 1 | 15 | 2012-07-31 | 2012-08-13 | 12 | 9 | 75%
Release 1 | 14 | 2012-07-17 | 2012-07-30 | 7 | 6 | 85.71%

## Team 2
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 3 | 1 | 2012-08-29 | 2012-09-12 | 14 | 14 | 100%
Release 3 | 2 | 2012-08-16 | 2012-08-29 | 13 | 15 | 115.4%
Release 2 | 1 | 2012-08-02 | 2012-08-15 | 13 | 12 | 92.31%
Release 1 | 4 | 2012-07-19 | 2012-08-01 | 12 | 12 | 100%
Release 1 | 3 | 2012-07-06 | 2012-07-18 | 13 | 13 | 100%
Release 1 | 2 | 2012-06-21 | 2012-07-04 | 12 | 10 | 83.33%
Release 1 | 1 | 2012-06-07 | 2012-06-20 | 17 | 15 | 88.24%
Release Z | 1 | 2012-05-24 | 2012-06-06 | 18 | 15 | 83.33%
Release Y | 1 | 2012-05-10 | 2012-05-23 | 18 | 18 | 100%
Release X | 8 | 2012-04-26 | 2012-05-09 | 22 | 17 | 77.27%
Release X | 7 | 2012-04-12 | 2012-04-25 | 16 | 22 | 137.5%

## Team 3
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 3 | 3 | 2012-09-06 | 2012-09-18 | 14 | 11 | 78.57%
Release 3 | 2 | 2012-08-23 | 2012-09-04 | 15 | 15 | 100%
Release 3 | 1 | 2012-08-09 | 2012-08-21 | 11 | 8 | 72.73%
Release 2 | 1 | 2012-07-26 | 2012-08-07 | 1 | 1 | 95%
Release 1 | 1 | 2012-07-11 | 2012-07-25 | 1 | 1 | 92%

## Team 4
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 2 | 3 | 2012-09-06 | 2012-09-18 | 10 | 8 | 80%
Release 2 | 2 | 2012-08-23 | 2012-09-04 | 12 | 10 | 83.33%
Release 2 | 1 | 2012-08-09 | 2012-08-21 | 9 | 7 | 77.78%
Release 1 | 2 | 2012-07-26 | 2012-08-07 | 8 | 8 | 100%
Release 1 | 1 | 2012-07-12 | 2012-07-24 |  |  | 84%

## Team 5
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 3 | 1 | 2012-09-05 | 2012-09-19 | 17 | 17 | 100%
Release 2 | 4 | 2012-08-22 | 2012-09-05 | 41 | 41 | 100%
Release 2 | 3 | 2012-08-08 | 2012-08-22 | 30 | 35 | 116.7%
Release 2 | 2 | 2012-07-25 | 2012-08-08 | 17 | 14 | 82.35%
Release 2 | 1 | 2012-07-11 | 2012-07-25 | 22 | 22 | 100%
Release 1 | 3 | 2012-06-13 | 2012-06-27 | 25 | 28 | 112%
Release 1 | 2 | 2012-05-30 | 2012-06-13 | 31 | 49 | 158%
Release 1 | 1 | 2012-05-16 | 2012-05-30 | 18 | 18 | 100%

## Team 6
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 1 | 6 | 2012-08-16 | 2012-08-30 | 15 | 15 | 100%
Release 1 | 5 | 2012-08-01 | 2012-08-16 | 25 | 20 | 80%
Release 1 | 4 | 2012-07-17 | 2012-08-01 | 20 | 18 | 90%
Release 1 | 3 | 2012-07-02 | 2012-07-17 | 16 | 16 | 100%

## Team 7
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 1 | 4 | 2012-08-30 | 2012-09-13 | 7 | 7 | 100% | Release 9/18/2012
Release 1 | 3 | 2012-08-16 | 2012-08-29 | 9 | 3 | 33.33%
Release 1 | 2 | 2012-08-02 | 2012-08-15 | 16 | 11 | 68.75%
Release 1 | 1 | 2012-07-19 | 2012-08-01 | 8 | 0 | 0%

## Team 8
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 4 | 1 | 2012-08-29 | 2012-09-12 | 29 | 23 | 79.31%
Release 3 | 1 | 2012-08-15 | 2012-08-29 | 24 | 22 | 91.67% | This sprint/release contained work identified and intiated by the delivery team during the transition of product owners.
Release 2 | 1 | 2012-08-02 | 2012-08-16 | 13 | 13 | 100% | Represents delivery stories and discovery stories that developers worked on.
Release 1 | 1 | 2012-07-17 | 2012-08-01 | 12 | 12 | 100%

## Team 9
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 2 | 1 | 2012-08-28 | 2012-09-11 | 3 | 3 | 100%
Release 2 | 2 | 2012-08-15 | 2012-08-28 | 4 | 3 | 75%
Release 1 | 3 | 2012-07-31 | 2012-08-14 | 7 | 6 | 85.71%
Release 1 | 2 | 2012-07-11 | 2012-07-24 | 5 | 5 | 100%

## Team 10
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 3 | 2 | 2012-08-29 | 2012-09-11 | 13 | 12 | 92.31%
Release 3 | 1 | 2012-08-15 | 2002-08-28 | 8 | 11 | 137.5%
Release 2 | 2 | 2012-08-01 | 2012-08-14 | 5 | 5 | 100%
Release 2 | 1 | 2012-07-18 | 2012-07-31 | 4 | 4 | 100%
Release 1 | 2 | 2012-06-29 | 2012-07-17 | 6 | 8 | 133.3% | Team completed two "uncommited" stories in addition to the ones to which they committed

## Team 11
Release | Sprint |  |  | Stories |  |  | Comments
| # | Start | End | Commited | Completed | Ratio
Release 4 | 2 | 2012-09-05 | 2012-09-19 | 9 | 6 | 66.67%
Release 3 | 2 | 2012-09-05 | 2012-09-19 | 10 | 7 | 70%
Release 3 | 1 | 2012-08-22 | 2012-09-05 | 4 | 4 | 100%
Release 2 | 1 | 2012-08-22 | 2012-09-05 | 6 | 5 | 83.33%
Release 1 | 4 | 2012-08-08 | 2012-08-22 | 10 | 9 | 90%
Release 1 | 3 | 2012-07-25 | 2012-08-08 | 13 | 13 | 100%
Release 1 | 2 | 2012-07-11 | 2012-07-25 | 7 | 3 | 42.86%
Release 1 | 1 | 2012-06-27 | 2012-07-11 | 10 | 10 | 100%